## Sheet1
Important Dates
Paper Video Upload | Nov 9th
Project Video Upload | Dec 14th
Project Report Upload | Dec 14th
|  |  |  | Dates of Completion |  |  |  | Date of Completion |  | Date of Completion
|  | Paper Video Presenter | Time | First Draft | Final Version | Project Video Presenter | Time | First Draft | Final Version | Project Report | First Draft | Final Version
Introduction and Business Case |  | Bharat | 2 | 2020-10-18 | 2020-10-30 | Bharat | 2 | 2020-11-15 | 2020-12-02 | Bharat | 2020-11-30 | 2020-12-05
EDA |  | Dylan | 2 | 2020-10-18 | 2020-10-30 | Dylan | 2 | 2020-11-15 | 2020-12-02
Data Preprocessing |  | Leonie | 2 | 2020-10-18 | 2020-10-30 | Leonie | 5 | 2020-11-15 | 2020-12-02
Applying Algorithms on Preprocessed Data |  |  |  | 2020-10-18 | 2020-10-30 |  |  | 2020-11-15 | 2020-12-02
Multiple Linear Regression |  | Bharat | 2 | 2020-10-18 | 2020-10-30 | Bharat | 2 | 2020-11-15 | 2020-12-02
Neural Networks |  | Leonie | 2 | 2020-10-18 | 2020-10-30 | Leonie | 2 | 2020-11-15 | 2020-12-02
RepTree |  | Jack | 2 | 2020-10-18 | 2020-10-30 | Jack | 2 | 2020-11-15 | 2020-12-02
Random Tree |  | Jack | 2 | 2020-10-18 | 2020-10-30 | Jack | 2 | 2020-11-15 | 2020-12-02
Summary of Findings |  | Bharat | 2 | 2020-10-18 | 2020-10-30 | Bharat | 3 | 2020-11-15 | 2020-12-02